## Project Alpha - Infrastructure
Date | Metric | Expected | Target | Complete | Owner
Description: | Infrastructure modernization initiative
Initiative Manager:
2025-05-31 | Database Upgrades | 9 | 84 | 7 | Admin User
2025-06-30 | Database Upgrades | 19 | 84 | 15 | Admin User
2025-07-31 | Database Upgrades | 28 | 84 | 24 | Admin User
2025-08-31 | Database Upgrades | 39 | 88 | 37 | Admin User
2025-09-30 | Database Upgrades | 49 | 88 | 48 | Admin User
2025-10-31 | Database Upgrades | 64 | 96 | 61 | Admin User
2025-11-30 | Database Upgrades | 75 | 96 | 74 | Admin User
2025-12-31 | Database Upgrades | 85 | 96 | 87 | Admin User
2026-01-31 | Database Upgrades | 96 | 96 | 96 | Admin User
2025-04-30 | Security Patching | 12 | 122 | 9 | Admin User
2025-05-31 | Security Patching | 24 | 122 | 18 | Admin User
2025-06-30 | Security Patching | 37 | 122 | 31 | Admin User
2025-07-31 | Security Patching | 49 | 122 | 46 | Admin User
2025-08-31 | Security Patching | 61 | 122 | 59 | Admin User
2025-09-30 | Security Patching | 73 | 122 | 73 | Admin User
2025-10-31 | Security Patching | 85 | 122 | 87 | Admin User
2025-11-30 | Security Patching | 98 | 122 | 99 | Admin User
2025-12-31 | Security Patching | 110 | 122 | 111 | Admin User
2026-01-31 | Security Patching | 122 | 122 | 122 | Admin User
2025-04-30 | Server Migration | 11 | 105 | 5 | Admin User
2025-05-31 | Server Migration | 21 | 105 | 12 | Admin User
2025-06-30 | Server Migration | 32 | 105 | 19 | Admin User
2025-07-31 | Server Migration | 44 | 110 | 28 | Admin User
2025-08-31 | Server Migration | 55 | 110 | 41 | Admin User
2025-09-30 | Server Migration | 71 | 118 | 54 | Admin User
2025-10-31 | Server Migration | 83 | 118 | 69 | Admin User
2025-11-30 | Server Migration | 94 | 118 | 82 | Admin User
2025-12-31 | Server Migration | 106 | 118 | 94 | Admin User
2026-01-31 | Server Migration | 118 | 118 | 118 | Admin User

## Project Beta - Customer Experie
Date | Metric | Expected | Target | Complete | Owner
Description: | Customer experience enhancement initiative
Initiative Manager:
2025-05-31 | Performance Optimization | 11 | 98 | 8 | Admin User
2025-06-30 | Performance Optimization | 22 | 98 | 17 | Admin User
2025-07-31 | Performance Optimization | 33 | 98 | 28 | Admin User
2025-08-31 | Performance Optimization | 45 | 102 | 39 | Admin User
2025-09-30 | Performance Optimization | 57 | 102 | 53 | Admin User
2025-10-31 | Performance Optimization | 71 | 106 | 66 | Admin User
2025-11-30 | Performance Optimization | 82 | 106 | 78 | Admin User
2025-12-31 | Performance Optimization | 94 | 106 | 90 | Admin User
2026-01-31 | Performance Optimization | 106 | 106 | 98 | Admin User
2025-04-30 | UI Redesign | 7 | 65 | 3 | Admin User
2025-05-31 | UI Redesign | 13 | 65 | 7 | Admin User
2025-06-30 | UI Redesign | 20 | 65 | 13 | Admin User
2025-07-31 | UI Redesign | 27 | 68 | 22 | Admin User
2025-08-31 | UI Redesign | 34 | 68 | 34 | Admin User
2025-09-30 | UI Redesign | 43 | 72 | 47 | Admin User
2025-10-31 | UI Redesign | 50 | 72 | 57 | Admin User
2025-11-30 | UI Redesign | 58 | 72 | 63 | Admin User
2025-12-31 | UI Redesign | 65 | 72 | 65 | Admin User
2026-01-31 | UI Redesign | 72 | 72 | 65 | Admin User

## Test Project
Date | Metric | Expected | Target | Complete | Owner
Description:
Initiative Manager: | Me
2025-10-23 | Attributes Delivered | 8 | 300 | 10
2025-11-23 | Attributes Delivered | 15 | 300 | 0
2025-12-23 | Attributes Delivered | 23 | 300 | 0
2026-01-23 | Attributes Delivered | 31 | 300 | 0
2026-02-23 | Attributes Delivered | 38 | 300 | 0
2026-03-23 | Attributes Delivered | 46 | 300 | 0
2026-04-23 | Attributes Delivered | 54 | 300 | 0
2026-05-23 | Attributes Delivered | 62 | 300 | 0
2026-06-23 | Attributes Delivered | 69 | 300 | 0
2026-07-23 | Attributes Delivered | 77 | 300 | 0
2026-08-23 | Attributes Delivered | 85 | 300 | 0
2026-09-23 | Attributes Delivered | 200 | 300 | 0
2026-10-23 | Attributes Delivered | 300 | 300 | 0
2025-10-23 | Widgets Delivered | 8 | 100 | 10 | Admin User
2025-11-23 | Widgets Delivered | 15 | 100 | 15 | Admin User
2025-12-23 | Widgets Delivered | 23 | 100 | 0 | Admin User
2026-01-23 | Widgets Delivered | 31 | 100 | 0 | Admin User
2026-02-23 | Widgets Delivered | 38 | 100 | 0 | Admin User
2026-03-23 | Widgets Delivered | 46 | 100 | 0 | Admin User
2026-04-23 | Widgets Delivered | 54 | 100 | 0 | Admin User
2026-05-23 | Widgets Delivered | 62 | 100 | 0 | Admin User
2026-06-23 | Widgets Delivered | 69 | 100 | 0 | Admin User
2026-07-23 | Widgets Delivered | 77 | 100 | 0 | Admin User
2026-08-23 | Widgets Delivered | 85 | 100 | 0 | Admin User
2026-09-23 | Widgets Delivered | 92 | 100 | 0 | Admin User
2026-10-23 | Widgets Delivered | 100 | 100 | 0 | Admin User

## Summary
Progress Tracker Export Summary
Export Date: | 2025-10-23T21:33:32.263Z
Total Projects: | 4
Project Name | Description | Initiative Manager
Another Project |  | EZ Geez
Project Alpha - Infrastructure Modernization | Infrastructure modernization initiative
Project Beta - Customer Experience | Customer experience enhancement initiative
Test Project |  | Me